## Tecnova
Tecnova Project Status
| Scope | Status @ 8 th June | Status @ 19th June | Status @ 5th Aug | users | Comments | Time Lines to complete
Applications | [6 empty] | Start date | End Date
1 | Application for Automate delivery quotation mails between merchant/planning/Procument | Done | Done | Done | HL Planners / merchants & procument | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS
2 | Application for Delivery Quotation (Merchant/Planner/Procument) / SAP sales order data setting | 50 % complete | 50 % complete | 50 % complete | HL Planners / merchants & procument | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS | 2015-08-06 | 2015-08-10 | 4
3 | Application for PROJECTION Management | pending | pending | pending | Planning / merchants / procument |  | 2015-08-11 | 2015-08-14 | 3
4 | Application for Plant Capacity Management | pending | pending | pending | Planning |  | 2015-08-11 | 2015-08-14 | 3
5 | Application for Automate Production order Number Creation | Pending | Pending | Pending |  |  | 2015-08-17 | 2015-08-20 | 3
| Application for Automate Recipe allocation | pending | pending | pending |  |  | 2015-08-21 | 2015-08-23 | 2
Reports
| Scope | Status @ 8 th June | Status @ 19th June | Status @ 5th Aug | users | Comments | Time Lines to complete
1 | Respond time for delivery quotation (Merchant/Planner/Procument) | Done | Done | Done | HL Planners | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS
2 | Week wise Dye Plan | Done | Done | Done | HL Planners | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS
3 | Weekly knitting plan | Done | Done | Done | HL Planners | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS
4 | Weekly Short lead time orders | Done | Done | Done | HL Planners | Waiting SAP data Uploading process & incresing the Speed of data downloading from SAP to PPS
5 | Weekly order type mix | Done | Done | Done | HL Planners
6 | Daily excess stock analysis | Done | Done | Done | Planning / merchants
7 | Daily shortage analysis | Done | Done | Done | Planning / merchants
8 | Weekly SJ/RIB, White/Mal order mix | Done | Done | Done | HL Planners
9 | Weekly OTD report | Done | Done | Done | Planning /Production / Merchants
10 | Daily OTD report | Done | Done | Done | Planning /Production / Merchants
11 | Delay & Thursday reports | Done | Done | Done | Planning /Production / Merchants
12 | daily OTD meeting report | Done | Done | Done | Planning /Production / Merchants
13 | FG Stock Analysis | Done | Done | Done | Planning / merchants
14 | Time taken from Dyeing to FG stock | Done | Done | Done | Planning /Production
19 | Greige Stocl Analysis & orders avaialbilty | pending | Done | Done | Planning / merchants | Sanath's Urgent report
24 | Possible weekly dying back log | pending | pending | Done | Planning /Production
31 | FG & WIP analysis | pending | pending | pending | Planning /Production / Merchants | Sanath's Urgent report | 2015-08-25 | 2015-08-26
32 | Advanced Delivered Qty & order placed in TJ report | pending | pending | pending | Planning /Production / Merchants | Sanath's Urgent report | 2015-09-11 | 2015-09-13
20 | 1st Bulk order report | pending | pending | pending | Planning /Production / Merchants |  | 2015-08-27 | 2015-08-28
22 | Possible Boil Outs for week | pending | pending | pending | Planning /Production |  | 2015-08-29 | 2015-09-02
21 | Pending Lab Dip/NPL/PP/Tec SPEC Report | pending | pending | pending | Planning /Production / Merchants |  | 2015-09-15 | 2015-09-17
27 | Daily stock code notification information | pending | pending | pending | Planning /Production |  | 2015-09-05 | 2015-09-10
29 | Weekly P4P allocation for print orders | pending | pending | pending | Planning /Production / QBL |  | 2015-08-20 | 2015-08-22
33 | Week wise dyed yarn plan | pending | pending | pending | Planning /Production |  | 2015-08-02 | 2015-08-10
30 | Weekly print plan for QBL | pending | pending | pending | Planning /Production / QBL |  | 2015-08-03 | 2015-08-05
28 | Weekly single lane Report | pending | pending | pending | Planning /Production |  | 2015-08-11 | 2015-08-12
26 | Weekly Knitting back log | pending | pending | pending | Planning /Production |  | 2015-08-14 | 2015-08-18
25 | Possible quality changes and gage changes | pending | pending | pending | Planning /Production |  | 2015-08-18 | 2015-08-20
23 | Possible awaiting greige for a week | pending | pending | pending | Planning /Production |  | 2015-08-21 | 2015-08-23
15 | Projection vs Actual Sales | 50 % complete | 50 % complete | 50 % complete | Planning / merchants |  | 2015-08-24 | 2015-08-26
16 | Projected revenue vs Actual sales revenue | 50% complete | 50% complete | 50 % complete | Planning / merchants |  | 2015-08-28 | 2015-08-31
17 | Impact of Capacity – row material due to deference of projection vs actual | pending | pending | pending | Planning / merchants |  | 2015-09-01 | 2015-09-05
18 | Unit wise Order receiving information comparing with projection | 50% complete | 50% complete | Done | Planning / merchants |  | 2015-09-18 | 2015-09-20

## sap1
| Scope | Status @ 5th Aug | users | Benefits | Time Lines to complete
[5 empty] | Start | End
1 | Rolls allocation in to PRD & automate batch splitting in to Dye M/C Lanes | Discussed with IT team (Kranthi).according to the new IT Structure change this should go through the SAP BA team & on 6th Aug Kranthi having meeting with us. | Mahee / Gayathri / Akila | Can reduse two Casual peaple permantly | Not yet plan | Not yet plan
2